| TASK NAME | START | DURATION | FINISH |
| --- | --- | --- | --- |
| Issue of full value instruction | 9th January 2026 | 1 day | 9.1.26 |
| Technical survey, design and drawings | 12th January 2026 | 4 weeks | 6.2.26 |
| Customer approval of drawings and finishes | 9th February 2026 | 2 weeks | 20.2.26 |
| Equipment manufacture inc. additional for resident planning | 23rd February 2026 | 17 weeks | 19.6.26 |
| Delivery into UK | 22nd June 2026 | 1 week | 26.6.26 |
| Lift unavailable for service | 29th June 2026 | 40 days | 21.8.26 |
| Site preparation and existing equipment removal | 29th June 2026 | 1 week | 3.7.26 |
| Install new lift | 6th July 2026 | 5 weeks | 7.8.26 |
| Making good | 10th August 2026 | 4 days | 13.8.26 |
| Test, commission, witness and items | 12th August 2026 | 3 days | 14.8.26 |
| Witness, test and items | 17th August 2026 | 2 days | 18.8.26 |
| Hand over to customer | 10th August 2026 | 1 day | 19.8.26 |